## Executive Summary
CBS DC-DR DAG Consolidation Plan: 7 → 3-4 DAGs
CURRENT STATE: 7 DAGs
DAG | Schedule | Tables | Sum Time (min) | Actual Time (min)
P0 | 10:15 AM | 3 | 21 | 24
P1 | 10:15 AM | 14 | 121 | 130
P2 | 10:15 AM | 77 | 91.5 | 140
P3 | 3:00 AM | 4 | 29 | 26
P4 | 7:00 AM | 36 | 226 | 250
P5 | 3:30 PM | 72 | 295 | 310
P6 | 5:00 AM | 17 | 185 | 170
TOTAL |  | 223 | 968.5 | 1050
PROPOSED CONSOLIDATION PLANS
3-DAG Plan: Sequential Windows |  | RECOMMENDED | 4-DAG Plan: Balanced Windows |  | RECOMMENDED | 3-DAG Alt: Lighter AM + Heavy Day |  | ALTERNATIVE
DAG Group | Tables | Est. Time | DAG Group | Tables | Est. Time | DAG Group | Tables | Est. Time
P3+P6+P4 | 57 | 7h 55m | P3+P6 | 21 | 3h 51m | P3+P6 | 21 | 3h 51m
P0+P1+P2 | 94 | 4h 12m | P4 | 36 | 4h 4m | P0+P1+P2+P4 | 130 | 8h 16m
P5 | 72 | 5h 19m | P0+P1+P2 | 94 | 4h 12m | P5 | 72 | 5h 19m
Total DAGs: | 3 |  | P5 | 72 | 5h 19m | Total DAGs: | 3
|  |  | Total DAGs: | 4

## 3-DAG Plan (Recommended)
3-DAG PLAN: Sequential Execution Windows
STATUS: RECOMMENDED
Groups all early-AM DAGs (P3+P6+P4) into one batch, merges the three 10:15 AM DAGs (P0+P1+P2), and keeps P5 standalone. Creates clean sequential non-overlapping execution windows across the day.
DAG Mapping: Old → New
New DAG Name | Proposed Schedule | Contains Old DAGs | # Tables | Sum Avg Time (min) | Est. Duration | Est. Start | Est. End | Window | Status
DAG-1: Early Morning Batch | 3:00 AM | P3 + P6 + P4 | 57 | 440 | 7h 55m | 3:00 AM | 10:55 AM | 3:00 AM – 10:55 AM | HEAVY
DAG-2: Mid-Day Batch | 10:15 AM | P0 + P1 + P2 | 94 | 233.5 | 4h 12m | 10:15 AM | 2:27 PM | 10:15 AM – 2:27 PM | MODERATE
DAG-3: Afternoon Batch | 3:30 PM | P5 | 72 | 295 | 5h 19m | 3:30 PM | 8:49 PM | 3:30 PM – 8:49 PM | MODERATE
Table Breakdown per New DAG
DAG-1: Early Morning Batch (P3+P6+P4)
Old DAG | Table Name | Avg Time (min)
P3 | gldm | 7
P3 | mnfh | 5
P3 | tffm | 4
P3 | ed2p | 13
P6 | gect | 15
P6 | gl01 | 9
P6 | gl02 | 11
P6 | ACFH | 10
P6 | acsn | 14
P6 | cusm | 11
P6 | indu | 9
P6 | invm | 17
P6 | invb | 15
P6 | brhm | 10
P6 | ctpm | 4
P6 | cusvdd | 4
P6 | depp | 4
P6 | infz | 10
P6 | ACRH | 17
P6 | INCT | 20
P6 | ENBR | 5
P4 | ACRH | 9
P4 | cusvaa | 6
P4 | cumi | 7
P4 | tdrv | 4
P4 | colm | 3
P4 | racd | 7
P4 | incc | 9
P4 | ddrh | 4
P4 | ctam | 4
P4 | cuid | 6
P4 | cusvd1 | 6
P4 | cusvd4 | 7
P4 | acfr | 2
P4 | HLDT | 3
P4 | coem | 7
P4 | txop | 4
P4 | ifsc | 10
P4 | apym | 7
P4 | gect_src | 5
P4 | GLEB | 7
P4 | SVS_SIG_LINK | 4
P4 | insh | 7
P4 | empp | 3
P4 | gstc | 7
P4 | audt | 9
P4 | SVS_SIG_MTX | 11
P4 | mfld | 7
P4 | mfsq | 6
P4 | mfsv | 5
P4 | mfvd | 6
P4 | QERR | 6
P4 | TXTM | 4
P4 | uuid | 7
P4 | COLE | 8
P4 | CURH | 10
P4 | MCAD | 9
DAG-2: Mid-Day Batch (P0+P1+P2)
Old DAG | Table Name | Avg Time (min)
P0 | qith | 9
P0 | eftm | 6
P0 | prod | 6
P1 | CUSVEQ | 8
P1 | KYCS | 12
P1 | SORD | 7
P1 | ocri | 10
P1 | icdd | 9
P1 | RELM | 8
P1 | BORG | 6
P1 | RELP | 9
P1 | CASN | 7
P1 | CID3 | 4
P1 | IPRD | 14
P1 | icid | 9
P1 | ocid | 10
P1 | DPDD | 8
P2 | 77 tables (all ~1-3 min each) | 91.5 total
DAG-3: Afternoon Batch (P5)
Old DAG | Table Name | Avg Time (min)
P5 | PEHL | 4
P5 | CSKV | 2
P5 | GTEM | 5
P5 | NCSM | 3
P5 | LRPS | 1
P5 | TDSH | 6
P5 | TDSM | 5
P5 | NRTR | 3
P5 | NAMO | 5
P5 | BSRO | 4
P5 | CUSVGG | 7
P5 | + 61 more tables...

## 4-DAG Plan (Balanced)
4-DAG PLAN: Balanced Execution Windows
STATUS: RECOMMENDED
Separates P4 from the early AM batch since it's heavy (226 min). P3+P6 run pre-dawn, P4 gets its own 7 AM slot, P0+P1+P2 merge at 10:15 AM, P5 stays afternoon. Best balance of consolidation and risk.
DAG Mapping: Old → New
New DAG Name | Proposed Schedule | Contains Old DAGs | # Tables | Sum Avg Time (min) | Est. Duration | Est. Start | Est. End | Window | Status
DAG-1: Pre-Dawn Batch | 3:00 AM | P3 + P6 | 21 | 214 | 3h 51m | 3:00 AM | 6:51 AM | 3:00 AM – 6:51 AM | OK
DAG-2: Morning Batch | 7:00 AM | P4 | 36 | 226 | 4h 4m | 7:00 AM | 11:04 AM | 7:00 AM – 11:04 AM | OK
DAG-3: Mid-Day Batch | 10:15 AM | P0 + P1 + P2 | 94 | 233.5 | 4h 12m | 10:15 AM | 2:27 PM | 10:15 AM – 2:27 PM | MODERATE
DAG-4: Afternoon Batch | 3:30 PM | P5 | 72 | 295 | 5h 19m | 3:30 PM | 8:49 PM | 3:30 PM – 8:49 PM | MODERATE
Table Breakdown per New DAG
DAG-1: Pre-Dawn Batch (P3+P6)
Old DAG | Table Name | Avg Time (min)
P3 | gldm | 7
P3 | mnfh | 5
P3 | tffm | 4
P3 | ed2p | 13
P6 | gect | 15
P6 | gl01 | 9
P6 | gl02 | 11
P6 | ACFH | 10
P6 | acsn | 14
P6 | cusm | 11
P6 | indu | 9
P6 | invm | 17
P6 | invb | 15
P6 | brhm | 10
P6 | ctpm | 4
P6 | cusvdd | 4
P6 | depp | 4
P6 | infz | 10
P6 | ACRH | 17
P6 | INCT | 20
P6 | ENBR | 5
DAG-2: Morning Batch (P4)
Old DAG | Table Name | Avg Time (min)
P4 | ACRH | 9
P4 | cusvaa | 6
P4 | cumi | 7
P4 | tdrv | 4
P4 | colm | 3
P4 | racd | 7
P4 | incc | 9
P4 | ddrh | 4
P4 | ctam | 4
P4 | cuid | 6
P4 | cusvd1 | 6
P4 | cusvd4 | 7
P4 | acfr | 2
P4 | HLDT | 3
P4 | coem | 7
P4 | txop | 4
P4 | ifsc | 10
P4 | apym | 7
P4 | gect_src | 5
P4 | GLEB | 7
P4 | SVS_SIG_LINK | 4
P4 | insh | 7
P4 | empp | 3
P4 | gstc | 7
P4 | audt | 9
P4 | SVS_SIG_MTX | 11
P4 | mfld | 7
P4 | mfsq | 6
P4 | mfsv | 5
P4 | mfvd | 6
P4 | QERR | 6
P4 | TXTM | 4
P4 | uuid | 7
P4 | COLE | 8
P4 | CURH | 10
P4 | MCAD | 9
DAG-3: Mid-Day Batch (P0+P1+P2)
Old DAG | Table Name | Avg Time (min)
P0 | qith | 9
P0 | eftm | 6
P0 | prod | 6
P1 | CUSVEQ | 8
P1 | KYCS | 12
P1 | SORD | 7
P1 | ocri | 10
P1 | icdd | 9
P1 | RELM | 8
P1 | BORG | 6
P1 | RELP | 9
P1 | CASN | 7
P1 | CID3 | 4
P1 | IPRD | 14
P1 | icid | 9
P1 | ocid | 10
P1 | DPDD | 8
P2 | 77 tables (all ~1-3 min each) | 91.5 total
DAG-4: Afternoon Batch (P5)
Old DAG | Table Name | Avg Time (min)
P5 | PEHL | 4
P5 | CSKV | 2
P5 | GTEM | 5
P5 | NCSM | 3
P5 | LRPS | 1
P5 | TDSH | 6
P5 | TDSM | 5
P5 | NRTR | 3
P5 | NAMO | 5
P5 | BSRO | 4
P5 | CUSVGG | 7
P5 | + 61 more tables...

## Timeline Comparison
Timeline Comparison: Current vs Proposed Plans
Plan / DAG Group | Duration | 2AM | 3AM | 4AM | 5AM | 6AM | 7AM | 8AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM
CURRENT: 7 Separate DAGs
P3 | 31m
P6 | 3h 20m
P4 | 4h 4m
P0 | 23m
P1 | 2h 11m
P2 | 1h 39m
P5 | 5h 19m
PROPOSED: 3-DAG Plan
DAG-1: P3+P6+P4 | 7h 55m
DAG-2: P0+P1+P2 | 4h 12m
DAG-3: P5 | 5h 19m
PROPOSED: 4-DAG Plan
DAG-1: P3+P6 | 3h 51m
DAG-2: P4 | 4h 4m
DAG-3: P0+P1+P2 | 4h 12m
DAG-4: P5 | 5h 19m

## Decision Matrix
Decision Matrix: Which Plan to Choose?
Criteria | Current (7 DAGs) | 3-DAG Plan | 4-DAG Plan | Weight
Number of DAGs to manage | 7 | 3 | 4 | High
Operational simplicity | Low — 7 separate schedules | High — 3 clean windows | Medium — 4 windows | High
Failure blast radius | Small — each DAG isolated | Medium — 57 tables in DAG-1 | Small-Med — max 94 tables | High
Longest single DAG runtime | ~310 min (P5) | ~475 min (DAG-1) | ~319 min (P5/DAG-4) | Medium
Risk of timeout (>8 hrs) | None | Low (DAG-1 is 7h55m) | None | High
Monitoring complexity | 7 alerts needed | 3 alerts needed | 4 alerts needed | Medium
Schedule conflicts | P0/P1/P2 overlap | No overlaps | Minor DAG-2/DAG-3 overlap | Medium
Re-run cost on failure | Low — small DAGs | High — DAG-1 is 8 hrs | Medium — max 4 hrs | High
Overall Recommendation |  | GOOD if stable infra | BEST BALANCE
FINAL RECOMMENDATION
Go with the 4-DAG Balanced Plan. It gives you the best trade-off: cuts DAG count nearly in half (7→4), keeps max runtime under 5.5 hours, avoids creating any risky mega-DAG, and maintains clean sequential execution windows. If infrastructure is very stable and you want maximum simplification, the 3-DAG plan is also viable but carries higher re-run risk.

## Implementation Plan
Implementation Checklist — 4-DAG Plan
# | Step | Details | New DAG Affected | Owner | Status
1 | Merge P3 + P6 configs | Combine dag_level_config_p3 and p6 table lists into new DAG-1 config. Set schedule to 3:00 AM. | DAG-1 |  | TODO
2 | Update DAG-1 job ID | Create new DC-DR job or update existing. Old IDs: 1546481103, 9999999999. | DAG-1 |  | TODO
3 | Keep P4 as DAG-2 | Rename dag_level_config_p4 to new naming convention. Schedule stays 7:00 AM. | DAG-2 |  | TODO
4 | Merge P0 + P1 + P2 configs | Combine all three 10:15 AM DAG configs into DAG-3. Total 94 tables. | DAG-3 |  | TODO
5 | Update DAG-3 job ID | Create new DC-DR job. Old IDs: 1546426061, 1546426069, 1546972952. | DAG-3 |  | TODO
6 | Keep P5 as DAG-4 | Rename dag_level_config_p5 to new naming convention. Schedule stays 3:30 PM. | DAG-4 |  | TODO
7 | Update monitoring/alerts | Reconfigure alerts for 4 DAGs instead of 7. Update SLA thresholds. | All |  | TODO
8 | Test in staging | Run all 4 new DAGs in staging environment. Validate table counts and timings. | All |  | TODO
9 | Parallel run | Run old 7-DAG and new 4-DAG configs in parallel for 1 week. Compare results. | All |  | TODO
10 | Cutover | Disable old 7 DAGs, enable new 4 DAGs in production. | All |  | TODO
11 | Decommission old configs | Archive old dag_level_config_p0 through p6. Update documentation. | N/A |  | TODO