## Executive Summary
CBS DC-DR DAG Consolidation — 7 to 4 DAGs ¦ P6 Standalone
Current State: 7 DAGs
DAG | Job ID | Schedule | Tables | Sum Avg (min) | Actual (min) | Max Table (min) | Note
P0 | 1546426061 | 10:15 AM | 3 | 21 | 24 | 9
P1 | 1546426069 | 10:15 AM | 14 | 121 | 130 | 14
P2 | 1546972952 | 10:15 AM | 77 | 91.5 | 140 | 3
P3 | 1546481103 | 3:00 AM | 4 | 29 | 26 | 13
P4 | 1546580445 | 7:00 AM | 36 | 226 | 250 | 11
P5 | 1546751992 | 3:30 PM | 72 | 295 | 310 | 8
P6 | 9999999999 | 5:00 AM | 17 | 185 | 170 | 20 | CRITICAL — Do not merge
Total |  |  | 223 | 968.5 | 1050 | 20
Proposed: 4-DAG Plan (Recommended)
New DAG | Contains | Schedule | Tables | Sum Avg (min) | Est. Duration | Start | End
DAG-1: Early Morning | P3 + P4 | 3:00 AM | 40 | 255 | 4h 35m | 3:00 AM | 7:35 AM
DAG-2: Mid-Day | P0 + P1 + P2 | 10:15 AM | 94 | 233.5 | 4h 12m | 10:15 AM | 2:27 PM
DAG-3: Afternoon | P5 | 3:30 PM | 72 | 295 | 5h 19m | 3:30 PM | 8:49 PM
DAG-4: Critical (P6) | P6 | 5:00 AM | 17 | 185 | 3h 20m | 5:00 AM | 8:20 AM
Key Metrics
DAGs reduced | 7 → 4
P6 status | Standalone — not merged
Longest DAG | DAG-3 (P5) at ~5h 19m
No DAG exceeds | 5.5 hours
Execution windows | 3 AM → 7:35 AM ¦ 5 AM → 8:20 AM (P6) ¦ 10:15 AM → 2:27 PM ¦ 3:30 PM → 8:49 PM

## 4-DAG Plan Detail
4-DAG Plan — Detailed Configuration
P6 (DAG-4): Critical tables — standalone, independent schedule and monitoring
New DAG | Schedule | Old DAGs | Tables | Sum Avg (min) | Est. Duration | Start | End | Execution Window | Risk
DAG-1: Early Morning | 3:00 AM | P3 + P4 | 40 | 255 | 4h 35m | 3:00 AM | 7:35 AM | 3:00 AM – 7:35 AM | Low
DAG-2: Mid-Day | 10:15 AM | P0 + P1 + P2 | 94 | 233.5 | 4h 12m | 10:15 AM | 2:27 PM | 10:15 AM – 2:27 PM | Low
DAG-3: Afternoon | 3:30 PM | P5 | 72 | 295 | 5h 19m | 3:30 PM | 8:49 PM | 3:30 PM – 8:49 PM | Moderate
DAG-4: Critical (P6) | 5:00 AM | P6 | 17 | 185 | 3h 20m | 5:00 AM | 8:20 AM | 5:00 AM – 8:20 AM | Critical
DAG-1: Early Morning (P3+P4)
Source DAG | Table Name | Avg Time (min)
P3 | gldm | 7
P3 | mnfh | 5
P3 | tffm | 4
P3 | ed2p | 13
P4 | ACRH | 9
P4 | cusvaa | 6
P4 | cumi | 7
P4 | tdrv | 4
P4 | colm | 3
P4 | racd | 7
P4 | incc | 9
P4 | ddrh | 4
P4 | ctam | 4
P4 | cuid | 6
P4 | cusvd1 | 6
P4 | cusvd4 | 7
P4 | acfr | 2
P4 | HLDT | 3
P4 | coem | 7
P4 | txop | 4
P4 | ifsc | 10
P4 | apym | 7
P4 | gect_src_derived | 5
P4 | GLEB | 7
P4 | SVS_SIG_LINKAGE | 4
P4 | insh | 7
P4 | empp | 3
P4 | gstc | 7
P4 | audt | 9
P4 | SVS_SIG_MATRIX | 11
P4 | mfld | 7
P4 | mfsq | 6
P4 | mfsv | 5
P4 | mfvd | 6
P4 | QERR | 6
P4 | TXTM | 4
P4 | uuid | 7
P4 | COLE | 8
P4 | CURH | 10
P4 | MCAD | 9
DAG-2: Mid-Day (P0+P1+P2)
Source DAG | Table Name | Avg Time (min)
P0 | qith | 9
P0 | eftm | 6
P0 | prod | 6
P1 | CUSVEQ | 8
P1 | KYCS | 12
P1 | SORD | 7
P1 | ocri | 10
P1 | icdd | 9
P1 | RELM | 8
P1 | BORG | 6
P1 | RELP | 9
P1 | CASN | 7
P1 | CID3 | 4
P1 | IPRD | 14
P1 | icid | 9
P1 | ocid | 10
P1 | DPDD | 8
P2 | 77 tables (avg ~1.2 min each) | 91.5
DAG-3: Afternoon (P5)
Source DAG | Table Name | Avg Time (min)
P5 | 72 tables (avg ~4.1 min each) | 295
DAG-4: Critical (P6) — DO NOT MERGE (P6)
Source DAG | Table Name | Avg Time (min)
P6 | gect | 15
P6 | gl01 | 9
P6 | gl02 | 11
P6 | ACFH | 10
P6 | acsn | 14
P6 | cusm | 11
P6 | indu | 9
P6 | invm | 17
P6 | invb | 15
P6 | brhm | 10
P6 | ctpm | 4
P6 | cusvdd | 4
P6 | depp | 4
P6 | infz | 10
P6 | ACRH | 17
P6 | INCT | 20
P6 | ENBR | 5

## 3-DAG Plan (Alternative)
3-DAG Plan — Maximum Consolidation ¦ P6 Standalone
Alternative option — merges 5 DAGs into one ~8h 48m batch. Higher re-run risk. Only if infrastructure is very stable.
New DAG | Schedule | Old DAGs | Tables | Sum Avg (min) | Est. Duration | Start | End | Execution Window | Risk
DAG-1: Day Batch | 3:00 AM | P3 + P4 + P0 + P1 + P2 | 134 | 488.5 | 8h 48m | 3:00 AM | 11:48 AM | 3:00 AM – 11:48 AM | High
DAG-2: Afternoon | 3:30 PM | P5 | 72 | 295 | 5h 19m | 3:30 PM | 8:49 PM | 3:30 PM – 8:49 PM | Low
DAG-3: Critical (P6) | 5:00 AM | P6 | 17 | 185 | 3h 20m | 5:00 AM | 8:20 AM | 5:00 AM – 8:20 AM | Critical

## Timeline
Execution Timeline — Current vs Proposed
DAG Group | Duration | 2AM | 3AM | 4AM | 5AM | 6AM | 7AM | 8AM | 9AM | 10AM | 11AM | 12PM | 1PM | 2PM | 3PM | 4PM | 5PM | 6PM | 7PM | 8PM | 9PM
Current: 7 DAGs
P3 | 31m | bar: 3AM
P6 (Critical) | 3h 20m | bar: 5AM to 8AM
P4 | 4h 4m | bar: 7AM to 11AM
P0 | 23m | bar: 10AM
P1 | 2h 11m | bar: 10AM to 12PM
P2 | 1h 39m | bar: 10AM to 11AM
P5 | 5h 19m | bar: 3PM to 8PM
Proposed: 4-DAG Plan
DAG-1: P3+P4 | 4h 35m | bar: 3AM to 7AM
DAG-4: P6 (Critical) | 3h 20m | bar: 5AM to 8AM
DAG-2: P0+P1+P2 | 4h 12m | bar: 10AM to 2PM
DAG-3: P5 | 5h 19m | bar: 3PM to 8PM
Alternative: 3-DAG Plan
DAG-1: P3+P4+P0+P1+P2 | 8h 48m | bar: 3AM to 11AM
DAG-3: P6 (Critical) | 3h 20m | bar: 5AM to 8AM
DAG-2: P5 | 5h 19m | bar: 3PM to 8PM

## Decision Matrix
Decision Matrix — P6 Standalone in All Plans
Criteria | Current (7 DAGs) | 4-DAG (Recommended) | 3-DAG (Alternative) | Importance
Number of DAGs | 7 | 4 | 3 | High
P6 isolation | Standalone | Standalone | Standalone | Critical
Longest single DAG | ~310 min (P5) | ~319 min (P5) | ~528 min (DAG-1) | High
Risk of >8 hr run | None | None | Yes — DAG-1 at 8h 48m | Critical
Failure blast radius | Small (max 77 tables) | Medium (max 94 tables) | Large (134 tables) | High
Re-run cost | Low | Medium (max ~4.5 hrs) | High (DAG-1 ~8.8 hrs) | High
Monitoring effort | 7 alerts | 4 alerts | 3 alerts | Medium
Schedule conflicts | P0/P1/P2 overlap | None | None | Medium
P6 monitoring priority | 1 of 7 | 1 of 4 | 1 of 3 | High
Recommendation
4-DAG Plan is the best choice. Halves DAG count (7 to 4), keeps P6 fully isolated, no DAG exceeds 5.5 hours, and all execution windows are clean and sequential. The 3-DAG plan is viable only if your infrastructure is very stable and you can accept an 8.8-hour re-run risk on failure.

## Implementation
Implementation Checklist — 4-DAG Plan
Rule: P6 (dag_level_config_p6) must not be merged. It keeps its own schedule, job ID, and monitoring.
# | Step | Details | Affected | Owner | Status | Priority
1 | Merge P3 into P4 | Combine dag_level_config_p3 tables into P4 config. New schedule: 3:00 AM. Total: 40 tables. | DAG-1 |  |  | High
2 | Create DAG-1 job | New DC-DR job replacing P3 (1546481103) and P4 (1546580445). Validate all 40 table configs. | DAG-1 |  |  | High
3 | Merge P0 + P1 + P2 | Combine three 10:15 AM configs into DAG-2. Total: 94 tables. Keep 10:15 AM schedule. | DAG-2 |  |  | High
4 | Create DAG-2 job | New DC-DR job replacing P0 (1546426061), P1 (1546426069), P2 (1546972952). | DAG-2 |  |  | High
5 | Rename P5 to DAG-3 | Rename dag_level_config_p5. Schedule stays 3:30 PM. No table changes. | DAG-3 |  |  | Medium
6 | P6 to DAG-4 (no merge) | Rename only. Do not merge any tables. Keep job ID, schedule (5 AM), all configs. | DAG-4 (P6) |  |  | Critical
7 | P6 priority monitoring | Dedicated alerts, faster thresholds, auto-escalation on failure. | DAG-4 (P6) |  |  | Critical
8 | Update all monitoring | Reconfigure for 4 DAGs. Set SLA thresholds per DAG. | All |  |  | High
9 | Staging validation | Run all 4 DAGs in staging. Validate table counts, timing, P6 independence. | All |  |  | High
10 | Parallel run (1 week) | Run old 7-DAG and new 4-DAG side by side. Compare sync counts and timing. | All |  |  | High
11 | Production cutover | Disable old DAGs. Enable new 4 DAGs. Verify P6 critical tables first. | All |  |  | Critical
12 | Decommission old configs | Archive dag_level_config_p0 through p5 (not p6). Update documentation. | N/A |  |  | Medium